## Sheet1
AIRPORT IMPROVEMENT PROGRAM PROJECTS UPDATE
As of January 27, 2022 ¦ Financials generated January 21, 2022
* | BNIA - AIP PROJECTS
Obstruction Removal - Obstruction Study - Phase I
Ellipse No: 22789 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant 102-2019 | 83133 |  | 54574.5
Start Date: August 2019 |  |  | NYSDOT PIN 5A00.23 | 13855.5 |  | 8052
Scheduled End Date: June 2021 |  |  | Future PFC | 13855.5 |  | 0
|  |  | Funding Total | 110844 |  | 62626.5 | 101376
| CURRENT STATUS | Awaiting comments on draft report from FAA; Can begin closeout after response.
NEXT STEPS
NOTES
CARES Act Grant for BUF
Ellipse No: 31624 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | AIP Grant 105-2020 | 21647814 |  | 19521386.35
Start Date: May 2020
Scheduled End Date: May 2024 |  |  | Funding Total | 21647814 |  | 19521386.35 | 19521386.35
CURRENT STATUS
NEXT STEPS
NOTES
CRRSA Act Grant for BUF
Ellipse No: 31628, 31630 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | General 108-2021 | 6443355 |  | 0
Start Date: May 2021 |  |  | Concessions 107-2021 | 526696 |  | 526696
Scheduled End Date: |  |  | Funding Total | 6970051 |  | 526696 | 526696
| CURRENT STATUS | Concessions grant closed.
NEXT STEPS
NOTES
American Rescue Plan Act of 2021 for BUF
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | General 109-2022 | 18037049 |  | 0
Start Date: |  |  | Concessions 110-2022 | 2106785 |  | 0
Scheduled End Date: |  |  | Funding Total | 20143834 |  | 0 | 0
| CURRENT STATUS | Grant executed December 16, 2021.
NEXT STEPS
NOTES
Runway 5/23 Improvements - Pavement Rehabilitation, Design
Ellipse No: 22804 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Slagle |  |  | AIP 106-2021 | 3024300 |  | 2577558
Start Date: September 2020 |  |  | FAA Amendment | 43750 |  | 0
Scheduled End Date: June 2022 |  |  | Future PFC | 332916.66 |  | 0
|  |  | Funding Total | 3400966.66 |  | 2577558 | 2799671
| CURRENT STATUS | 100% design completed
NEXT STEPS
NOTES
Runway 5/23 and Taxiway A Improvements - Phase I - Pavement Rehabilitation, Construction
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Slagle |  |  | AIP Entitlements FFY 2022 | 3618000 |  | 0
Start Date: January 2021 |  |  | Supplemental Disc. | 26666666
Scheduled End Date: June 2025
|  |  | Funding Total | 30284666 |  | 0 | 0
| CURRENT STATUS | Bid opening held on January 20, 2022.
Lowest bidder is $4 million higher than estimate.
| NEXT STEPS | Final bid to be verified by January 27, 2022.
NOTES
Master Plan Update
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant FFY 2023
Start Date: |  |  | NYSDOT PIN
Scheduled End Date: |  |  | Future PFC |  |  | 0
Funding Total
CURRENT STATUS
NEXT STEPS
NOTES
Obstruction Removal - Environmental Assessment
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant FFY 2023
Start Date: |  |  | NYSDOT PIN
Scheduled End Date: |  |  | Future PFC |  |  | 0
Funding Total
CURRENT STATUS
NEXT STEPS
NOTES
General Aviation Apron and Taxiway P and Q Rehabilitation, Design
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: |  |  | AIP FFY 2023 | 0 |  | 0
Start Date: |  |  | Future NYSDOT | 0 |  | 0
Scheduled End Date: |  |  | Future PFC | 0 |  | 0
|  |  | NFTA Share | 0
|  |  | Funding Total | 1080000 |  | 0 | 9590
| CURRENT STATUS | Meeting to discuss scope was held April 20, 2021.
| NEXT STEPS | Engineering Department will identify needs and develop design scope.
Will review scope with FAA to identify construction schedule/funding.
NOTES
* | NFIA - AIP PROJECTS
Conduct Environmental Assessment - Parallel Taxiway Program
Ellipse No: 21512 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant 048-2018 | 91177.2 |  | 30592
Start Date: February 2018 |  |  | NYSDOT PIN 5902.22 | 5065.4 |  | 1329
Scheduled End Date: December 2021 |  |  | PFC 18-02-C-00-IAG | 5065.4 |  | 0
|  |  | Funding Total | 101308 |  | 31921 | 38427
| CURRENT STATUS | Internal revisions to draft report are being made.
| NEXT STEPS | Waiting on USAC approval/comments; draft will be submitted to NYADO once received
Request to extend period of performance due to FAA June 2022.
NOTES
Part 77 Obstruction Removal ¦ Design & Construction
Ellipse No: 21508 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel, D. Moran |  |  | AIP Grant 049-2018 | 1320278 |  | 1142619
Start Date: September 2018 (Construction) |  |  | NYSDOT PIN 5902.23 | 73349 |  | 58583
Scheduled End Date: January 2022 |  |  | PFC 18-02-C-00-IAG | 73349 |  | 63470
|  |  | Future Amendments | 2729
|  |  | Funding Total | 1469705 |  | 1264672 | 1286475
| CURRENT STATUS | Requested increase to design force account.
Received FAA approval for supplemental agreement.
| NEXT STEPS | Wetland monitoring required per NYSDEC for 1 more year ending January 2023.
Request to extend the period of performance due to FAA July 2022.
NOTES
Part 77 Obstruction Removal ¦ Off-Airport Acquire Land/Easements, Design
Ellipse No: 21518 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel, J. Diebold |  |  | AIP Grant 051-2019 | 89172 |  | 80850
Start Date: October 2019 |  |  | NYSDOT PIN 5902.25 | 4954 |  | 0
Scheduled End Date: June 2021 |  |  | Future PFC | 4954 |  | 0
|  |  | Funding Total | 99080 | 99080 | 80850 | 96351
| CURRENT STATUS | Final report submitted to FAA on May 12, 2021 - awaiting comments.
Awaiting scope change approval.
NEXT STEPS
NOTES
Rehabilitate Taxiway D, Design
Ellipse No: 21514 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Diebold |  |  | AIP Grant 050-2019 | 315000 |  | 306997
Start Date: July 2019 |  |  | NYSDOT PIN 5902.24 | 17500 |  | 14148
Scheduled End Date: January 2021 |  |  | Future PFC | 17500 |  | 0
|  |  | Funding Total | 350000 |  | 321145 | 341108
| CURRENT STATUS | FAA grant closeout approved January 13, 2022.
NEXT STEPS
NOTES
CARES Act Grant for IAG
Ellipse No: 31625 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | AIP Grant 052-2020 | 1890589 |  | 0
Start Date: May 2020 | [5 empty] | 0
Scheduled End Date: May 2024 |  |  | Funding Total | 1890589 |  | 0 | 0
| CURRENT STATUS | Inactive status
NEXT STEPS
NOTES
CRRSA Act Grant for IAG
Ellipse No: 31629, 31631 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | General 055-2021 | 1456382 |  | 0
Start Date: May 2021 |  |  | Concession 054-2021 | 26143 |  | 26143
Scheduled End Date: |  |  | Funding Total | 1482525 |  | 26143 | 26143
| CURRENT STATUS | Concessionaire grant closed out.
NEXT STEPS
NOTES
American Rescue Plan Act of 2021 for IAG
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Kempner |  |  | General 056-2022 | 2016356 |  | 0
Start Date: |  |  | Concessions 057-2022 | 104573 |  | 0
Scheduled End Date: |  |  | Funding Total | 2120929 |  | 0 | 0
| CURRENT STATUS | Grant excecuted on December 16, 2021.
| NEXT STEPS | PA circulating for concessions funds.
NOTES
Rehabilitate Taxiway D, Construction
Ellipse No: 21521 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Diebold |  |  | AIP Grant 053-2021 | 5501741 |  | 0
Start Date: January 2021
Scheduled End Date: April 2023
|  |  | Funding Total | 5501741 |  | 0 | 3719
| CURRENT STATUS | FAA award for concurrence and NTP completed September 2021.
| NEXT STEPS | Construction is scheduled to start March 2022.
NOTES
Part 77 Off-Airport Land Easements, Land Acquisition and Tree Removal within the 10L RPZ, Design
Ellipse No: 22795 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel, J. Diebold |  |  | AIP FFY 2023 | 180000 |  | 0
Start Date: February 2020 |  |  | Future NYSDOT | 10000 |  | 0
Scheduled End Date: 2023 |  |  | Future PFC | 10000 |  | 0
|  |  | Funding Total | 200000 |  | 0 | 15078
CURRENT STATUS
NEXT STEPS
NOTES
Pavement Management Program Update
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: |  |  | AIP FFY 2022 | 162000 |  | 0
Start Date: |  |  | Future NYSDOT | 9000 |  | 0
Scheduled End Date: |  |  | Future PFC | 9000 |  | 0
|  |  | Funding Total | 180000 |  | 0 | 0
| CURRENT STATUS | Consultant selection and grant application due January 31, 2022.
NEXT STEPS
NOTES
Taxiway D Realignment and Extension, Environmental Assessment
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: |  |  | AIP FFY 2022 | 450000 |  | 0
Start Date: |  |  | Future NYSDOT | 25000 |  | 0
Scheduled End Date: |  |  | Future PFC | 25000 |  | 0
|  |  | Funding Total | 500000 |  | 0 | 0
| CURRENT STATUS | Discussed with FAA the need for one NEPA action (EA w/military)
| NEXT STEPS | Design 2024; Construction 2026
| NOTES | Coordinating changes with USAF due to aligned taxiway design complications
Application usually due January 30th, but FAA granted an extension.
* | BNIA PASSENGER FACILITY CHARGE (PFC) PROGRAM
PFC APPLICATION NO. 13 (16-13-C-03-BUF) | [5 empty] | FAD Date: June 28, 2016
Airfield Signage Replacement - Runway 5/23 and Taxiway A ¦ PFC Project B-7
Engineering Project No: BA1716 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Ellipse No: 22718 & 22724 |  |  | PFC 16-13-C-03-BUF | 1875000 |  | 597079
Project Manager: D. Lupp, J. Diebold |  |  | PFC Amendment | 516000 |  | 0
Start Date: February 2018 |  |  | Project Total | 2391000 |  | 597079 | 597079
Scheduled End Date: February 2023
| CURRENT STATUS | Project 22718 is closed.
| NEXT STEPS | Airfield signange Replacement for RW 5/23 will occur during construction phases.
NOTES
PFC APPLICATION NO. 14 (18-14-C-03-BUF) | [5 empty] | FAD Date: June 5, 2018
Aircraft Deicing Containment Facility Expansion, Design and Construction
Ellipse No: 22691 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Diebold |  |  | PFC 18-14-C-03-BUF | 7576000 |  | 2032901
Start Date: May 2017 |  |  | PFC Amendment | 1955173
Scheduled End Date: December 2021 |  |  | Project Total | 9531173 |  | 2032901 | 7584168
| CURRENT STATUS | Construction is on schedule. 98% complete.
| NEXT STEPS | Justification to replace snow melt pad with snow melter was submitted to FAA in December 2020.
NOTES
ARFF Equipment - Replace F-8
Ellipse No: 22794 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: B. Major |  |  | PFC 18-14-C-03-BUF | 1000000 |  | 1000000
Start Date: December 2018 |  |  | PFC Amendment | 329568 |  | 0
Scheduled End Date: June 2021 |  |  | Project Total | 1329568 |  | 1000000 | 1329568
| CURRENT STATUS | PFC amendment increase will require air carrier consultation.
NEXT STEPS
NOTES
Snow Removal Equipment
Ellipse No: Various |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Guarino |  |  | PFC 18-14-C-03-BUF | 1469308 |  | 226861
Start Date:
Scheduled End Date: |  |  | Project Total | 1469308 |  | 226861 | 226861
CURRENT STATUS
NEXT STEPS
NOTES
SIDA Training System
Ellipse No: 22793 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Reilly, J. Godinez |  |  | PFC 18-14-C-03-BUF | 128960 |  | 0
Start Date: March 2019
Scheduled End Date: December 2021 |  |  | Project Total | 128960 |  | 0
| CURRENT STATUS | Status meeting held on December 10th; Launch date change due to physical and data migration constraints.
NEXT STEPS
NOTES
Terminal Expansion - Baggage Claim Area Construction
Ellipse No: 22728 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Moran |  |  | Bond/PFC 18-14-C-03-BUF | 60744852 |  | 38094383
Start Date: November 2018 |  |  | NYSDOT | 1500000 |  | 0
Scheduled End Date: April 2022 |  |  | NYSDOT Multi-Modal | 300000 |  | 0
|  |  | National Fuel | 115565 |  | 0
|  |  | ADF | 1734907 |  | 0
|  |  | Project Total | 64395324 | 0 | 38094383 | 63902100
CURRENT STATUS
NEXT STEPS
NOTES
Snow Removal Equipment Building, Design
Ellipse No: 22737 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Slagle |  |  | PFC 18-14-C-03-BUF | 1092532.82 |  | 53002
Start Date: October 2018 |  |  | ADF | 538113.18 |  | 26243
Scheduled End Date: On hold |  |  | Project Total | 1630646 |  | 79245 | 82768
| CURRENT STATUS | Project will be on hold for the immediate future.
| NEXT STEPS | Payroll expense element overbudget. Expense elements should be suspended.
NOTES
Rehabilitate Public Access Apron, Design
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Diebold |  |  | PFC 18-14-C-03-BUF
Start Date: 2023
Scheduled End Date:
|  |  | Project Total | 0 |  | 0
| CURRENT STATUS | Will delete this project from application. Project scope has expanded.
NEXT STEPS
NOTES
Wildlife Hazard Assessment and Management Plan Update
Ellipse No: 22722 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant 094-2017 | 62810 |  | 62810
Start Date: January 2017 |  |  | PFC 18-14-C-03-BUF | 10468 |  | 10468
Scheduled End Date: January 2021 |  |  | NYSDOT PIN 5A00.15 | 10468 |  | 9690
|  |  | Project Total | 83746 |  | 82968 | 83747
| CURRENT STATUS | AIP grant closed.
| NEXT STEPS | Amend down PFC share to actual cost.
NOTES
PFC Planning and Program Administration
Ellipse No: 22309 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: N/A |  |  | PFC 18-14-C-03-BUF | 200000 |  | 147426
Start Date: 2018
Scheduled End Date: 2022 |  |  | Project Total | 200000 |  | 147426 | 147426
CURRENT STATUS
NEXT STEPS
NOTES
* | NFIA PASSENGER FACILITY CHARGE (PFC) PROGRAM
PFC APPLICATION NO. 1 (17-01-C-00-IAG) | [5 empty] | FAD Date: August 22, 2017
| CURRENT STATUS | Closeout PFC appplication next quarter.
PFC APPLICATION NO. 2 (18-02-C-00-IAG) | [5 empty] | FAD Date: September 27, 2018
Parallel Taxiway Program, Environmental Study
Ellipse No: 21512 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel |  |  | AIP Grant 048-2018 | 91177.2 |  | 30592
Start Date: February 2018 |  |  | NYSDOT PIN 5902.22 | 5065.4 |  | 1329
Scheduled End Date: December 2021 |  |  | PFC 18-02-C-00-IAG | 5065.4 |  | 0
|  |  | Funding Total | 101308 |  | 31921 | 38427
| CURRENT STATUS | Internal revisions to draft report are being made.
| NEXT STEPS | Waiting on USAC approval/comments; draft will be submitted to NYADO once received
Request to extend the period of performance due to FAA June 2022.
NOTES
Part 77 Obstruction Removal ¦ Design & Construction
Ellipse No: 21508 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel, D. Moran |  |  | AIP Grant 049-2018 | 1320278 |  | 1142619
Start Date: September 2018 (Construction) |  |  | NYSDOT PIN 5902.23 | 73349 |  | 57199.11
Scheduled End Date: December 2021 |  |  | PFC 18-02-C-00-IAG | 73349 |  | 58701
|  |  | Future Amendments | 2729
|  |  | Funding Total | 1469705 |  | 1258519.11 | 1286475
| CURRENT STATUS | Requested increase to design force account.
Received FAA approval for supplemental agreemnt.
| NEXT STEPS | Wetland monitoring required per NYSDEC for one more year ending January 2023.
Request to extend the period of perforamnce due to FAA July 2022.
NOTES
Airfield Lighting and Signage
Ellipse No: 21519 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Diebold |  |  | PFC 18-02-C-01-IAG | 3128219 |  | 1453
Start Date: January 2020
Scheduled End Date: January 2021 |  |  | Project Total | 3128219 |  | 1453 | 2062
| CURRENT STATUS | Project on hold.
| NEXT STEPS | Will request AIP funds in FFY 2024, possibly tie into Runway 6/24 project.
NOTES
PFC Administration
Ellipse No: 21504 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: N/A |  |  | PFC 18-02-C-00-IAG | 32000 |  | 31935
Start Date: January 2018
Scheduled End Date: January 2024 |  |  | Project Total | 32000 |  | 31935 | 31935
CURRENT STATUS
NEXT STEPS
NOTES
PFC APPLICATION NO. 3
| CURRENT STATUS | Proposed projects:
Install Perimeter Fencing, Environmental Phase - $17,320
Wildlife Hazard Assessment - $4,154
Snow Removal Equipment - Snowblower, Multi-Task Vehicle, Material Spreader - $848,164
PFC Planning and Program Administration - $32,000
Total Requested - $901,638
| NEXT STEPS | PFC Application No. 3 draft application under FAA review.
NOTES
* | NYSDOT Aviation Capital Grant Program
NFIA Install Perimeter Fence, Runway 10L Protection Zone | [6 empty] | 2017 Award
Ellipse No: 21515 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: S. Brenzel/ S. Slagle |  |  | NYSDOT PIN 5902.53 | 507246
Start Date: August 2019 |  |  | Future PFC No. 3 | 17320
Scheduled End Date: December 2022 |  |  | Future PFC No. 4 | 109491
|  |  | Funding Total | 524566 |  |  | 118111
| CURRENT STATUS | New York State Fence, Inc. bid approved by board December 9, 2021.
NEXT STEPS
NOTES
BNIA Security Checkpoint Expansion (Terminal Expansion, Baggage Claim Area) | [6 empty] | 2017 Award
Ellipse No: 22728 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: D. Moran |  |  | NYSDOT PIN 5A00.98 | 1500000
Start Date: November 2018 |  |  | PFC 18-14-C-03-BUF | 1751995
Scheduled End Date: April 2022 |  |  | Funding Total | 3251995
| CURRENT STATUS | NYSDOT drawdown will occur at project closeout.
NEXT STEPS
NOTES
BNIA Parking Expansion Project - Buell Avenue - Design & Construction | [6 empty] | 2018 Award
Ellipse No: 22785 |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: J. Wojcik |  |  | NYSDOT PIN 5A00.97 | 1500000 |  | 0
Start Date: September 2019 |  |  | NFTA | 1337740.9 |  | 0
Scheduled End Date: May 2022 |  |  | Funding Total | 2837740.9 |  | 0 | 1602442
| CURRENT STATUS | Paving will not be complete until next spring due to weather conditions.
NEXT STEPS
NOTES
BNIA Passenger Terminal Generator | [6 empty] | 2019 Award
Ellipse No: |  |  |  | Funding Breakdown |  | Applied for to Date | Expenditure to Date
Project Manager: |  |  | NYSDOT | 1295513 |  | 0
Start Date: |  |  | NFTA | 555220 |  | 0
Scheduled End Date: |  |  | Funding Total | 1850733 |  | 0
| CURRENT STATUS | Award announced on October 18, 2021.
Awaiting contract from NYSDOT.
NEXT STEPS
NOTES
2020 Aviation Capital Grant Program
Applications for $230 million Upstate Airport Economic Development and Revitalization submitted September 15, 2021.
Solicitation for $25 million program to be announced.
Previous Meeting Attendees (December 8, 2021):
A. Adams, J. Cox, W. Dubashi, M. Hernandez, D. Kempner, D. Lupp, A. Lenda, J. O'Hearn, M. Perla, B. Roth, C. Ruminski, L. Weitz