## IAG 2021-2026
Niagara Falls International Airport
Capital Improvement Program
Airport: | Niagara Falls International Airport |  |  |  |  | State: | New York |  |  | NPIAS #: | 0086 |  |  | LOC ID: | IAG | Date: | 2020-12-11
Project Description/Narrative |  | NPR | Work Code | Federal Funds ($1,000) |  |  |  |  | State Matching Funds ($1,000) | Local ($1,000) |  | State funded only | Totals ($1,000) | Environmental Type | Environmental Status | Comments
|  |  |  | Entitlement | Cargo Entitlement | Discretionary | State Apportion. | Supplementary Discretionary |  | PFC | Other
2021
Rehabilitate Taxiway D, Construction |  | 76 | RC/RE TW IM | 4951664.685 |  |  |  |  | 275092.4825 | 275092.4825 |  |  | 5501849.65 |  | Approved 2/19 | Carryover Passenger Entitlement Funds Local Share - Future PFC Application
Non-AIP Projects
Install Perimeter Fencing in Runway 10L Protection Zone, Design/Construction | [9 empty] | 109491.2 |  | 437964.8 | 547456 |  | Ongoing | NYSDOT AIR '99 & Future PFC
Snow Removal Equipment - Multi-Task Vehicle | [9 empty] | 159664 |  | 638656 | 798320 |  | Approved 5/19 | Future PFC Application No. 3
Total FY2021 |  |  |  | 4951664.685 | 0 | 0 | 0 | 0 | 275092.4825 | 544247.6825 | 0 | 1076620.8 | 6847625.65
2022
Part 77 Off-Airport Land Acquisition 10L RPZ and Obstruction Removal Design & Permits. |  | 88 | SP RW OB | 180000 |  |  |  |  | 10000 | 10000 |  |  | 200000 |  | Approved 9/17 | Local Share - Future PFC Application
Pavement Management Program Update |  | 73 | PL MA MS | 162000 |  |  |  |  | 9000 | 9000 |  |  | 180000 |  | Future 2021 | Local Share - Future PFC Application
Non-AIP Projects
Snow Removal Equipment - Snowblower, Material Spreader | [9 empty] | 688500 |  |  | 688500 |  | Approved 5/19 | Future PFC Application No. 3
Total FY2022 |  |  |  | 342000 | 0 | 0 | 0 | 0 | 19000 | 707500 | 0 | 0 | 1068500
2023
Part 77 Off-Airport Obstruction Removal 10L RPZ, Construction |  | 88 | SP RW OB | 225000 |  |  |  |  | 12500 | 12500 |  |  | 250000 |  | Approved 9/17 | Local Share - Future PFC Application
Runway 6/24 Rehabilitation, Design |  | 81 | RE RW IM | 630000 |  |  |  |  | 35000 | 35000 |  |  | 700000 |  | Future 2021 | Local Share - Future PFC Application
Wildlife Hazard Management Plan Update |  | 75 | PL MA WH | 74776.5 |  |  |  |  | 4154.25 | 4154.25 |  |  | 83085 |  | Future 2021 | Future PFC Application No. 3
Airfield Lighting and Signage, Construction |  | 44 | ST OT SG | 2625300 |  |  |  |  | 145850 | 145850 |  |  | 2917000 |  | Approved 6/18 | PFC Application No. 2
Total FY2023 |  |  |  | 3555076.5 | 0 | 0 | 0 | 0 | 197504.25 | 197504.25 | 0 | 0 | 3950085
2024
Part 77 Off-Airport Land Easements and Design 10L Non-RPZ |  | 88 | SP RW OB | 270000 |  |  |  |  | 15000 | 15000 |  |  | 300000 |  | Approved 9/17 | Local Share - Future PFC Application
Total FY2024 |  |  |  | 270000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 300000
2025
Runway 6/24 Rehabilitation, Construction |  | 81 | RE RW IM | 2800000 |  | 6200000 |  |  | 500000 | 0 | 500000 |  | 10000000 |  | Future 2021 | Local Share - Future PFC Application
Total FY2025 |  |  |  | 2800000 | 0 | 6200000 | 0 | 0 | 500000 | 0 | 500000 | 0 | 10000000
2026
Part 77 Off-Airport Obstruction Removal 10L Non-RPZ, Construction |  | 88 | SP RW OB | 450000 |  |  |  |  | 25000 |  | 25000 |  | 500000 |  | Approved 9/17 | Local Share - Future PFC Application
Parallel Taxiway Program – Design (Taxiway B, B1, B2, and Former E) |  | 76 | RE TW IM | 1000000 |  | 2705000 |  |  | 195000 |  | 195000 |  | 3900000 |  | Ongoing EA | Local Share - Future PFC Application
Total FY2026 |  |  |  | 1450000 | 0 | 2705000 | 0 | 0 | 220000 | 0 | 220000 | 0 | 4400000

## Sheet2
Environmental type
Catex
Short EA
EA
EIS